## Sheet1
Task | Start Date | End Date | Duration
Data Collection | 2025-01-06 | 2025-01-15 | 10
Data Preprocessing /Data Transformation | 2025-01-14 | 2025-01-22 | 9
Proposal Writing | 2025-01-23 | 2025-01-29 | 7
Proposal submission | 2025-02-01 | 2025-02-03 | 3
Preparing for mid-term Submission | 2025-02-06 | 2025-02-08 | 3
Preparing for Data Interpretation + Final Submission | 2025-02-11 | 2025-02-13 | 3